## Intro
Taboola Planning - Group B3
Preliminary Activities
Analysis
Test Release
Pre – GO LIVE!
GO LIVE!
Kick-off
IT insfrastructures
Set platforms and accesses
Analysis
Development
Testing
C.Care Users Training
Create Client Demo
Beta - Testing

## Taboola_MilestoneChart_v1.0
Completion Date | Milestone N° | Milestone Name | Duration | Assignee | Dependencies | Status | Comments
2022-03-02 | M-01 | Project Start | 1 Day | Project manager |  | Complete | Kick-off meeting with Stakeholders
2022-03-10 | M-02 | IT infrastructure | 1 Week | IT Infrastructure team |  | Complete | The complietion relies on the successful delivery of the following: - Preparation of Testing Environment - Preparation ProductionEnvironment
2022-03-10 | M-03 | Platforms & Accesses | 1 Week | DBA Team Security System Team |  | In Progess | The complietion relies on the successful delivery of the following: - Creation of all the required DBs - Setting and customization of users accesses - Security system check
2022-03-23 | M-04 | Chatbot Design | 4 Weeks | Business Analyst Team |  | Not Started | The complietion relies on the successful delivery of the following: - Get Business informations through Customer Care Interviewing - Drawing of all the required functional documents (like Functional Analysis and flowcharts)
2022-05-02 | M-05 | Chatbot Back-end Developing | 2 Weeks | Back-End Developers Team | M-04 | Not Started | The complietion relies on the successful delivery of the following: - Software back-end Programming
2022-05-02 | M-06 | Chatbot Front-end Developing | 2 Weeks | Visual Designer UX/UI Designer Front-end Developer | M-04 M-05 | Not Started | The complietion relies on the successful delivery of the following: - Software front-end Programming - UX/UI design - Graphic design
2022-06-13 | M-07 | Test Phase | 4 Weeks | Business Analyst Team Development Team | M-05 M-06 | Not Started | The complietion relies on the successful delivery of the following: - IT tests checklist OK - UAT tests checklist OK
2022-06-03 | M-08 | Customer Care User Training | 2 Weeks | Software Engineer Team Customer Care | M-05 M-06 | Not Started | The complietion relies on the successful delivery of the following: - Customer Care get all the required training to solve tech issues via Chat & Call center
2022-06-04 | M-09 | Create Client Demo | 2 Weeks | Video maker Busines Analyst Back-End Developers Team Front-end Developer | M-05 M-06 | Not Started | The complietion relies on the successful delivery of the following: - Creation and uploading of Video Tutorials and Documents that could be helpful for the customers
2022-07-14 | M-10 | Beta Tests | 4 Weeks | Business Analyst Team Development Team Customer Quality Manager | M-09 | Not Started | The complietion relies on the successful delivery of the following: - Beta tests checklist OK
2022-07-24 | M-11 | GO LIVE! | 1 Day | Development Team | M-010 | Not Started | The machine gets turn ON
CHATBOT - MILESTONES CHART

## ClickUp Milestones
CHATBOT - GANTT CHART

## WBS
Work breakdown Structure
Phase | Task | Estimation (days) | Level | Name | Responsible | Estimation | Discription
Preliminary Activities 1 | IT Infrastructure 1.1 | 16
|  |  | 0.042373 | The Log in screen | It Department | 2 | Designing a user-friendly log in page with all required elements
|  |  | 0.042384 | When a mandatory field is left empty | It Department | 2 | Show an error message “Please fill all mandatory fields”
|  |  | 0.042396 | When incorrect entry | It Department | 2 | Show an error message “You have entered an incorrect e-mail or password”
|  |  | 0.042407 | A Forgot password element | It Department | 2 | Redirecting the user into change your password page
|  |  | 0.042419 | A retrieve password screen | It Department | 2 | Redirect to retrieve password screen
|  |  | 0.042431 | Successful log in | It Department | 2 | after succesfully log in, the platform Redirect to main screen
|  |  | 0.042442 | A new user element | It Department | 2 | if the user dont have account, the platform redirect him to page to create new account
|  |  | 0.042454 | A log out screen | It Department | 2 | pressing on log out button and then it redirect you to the home screen
| Set platforms and accesses 1.2 | 9
|  |  | 0.043067 | chatbot pop up access | It Department | 3
|  |  | 0.043079 | make an icon for the chatbot in the screen | It Department | 1 | an icon that moves with you while checking the website
|  |  | 0.04309 | make a pop up messege for how can I help you | It Department | 1 | the message appears temporary every now and then to quicly access the chatbot
|  |  | 0.043102 | chatbot screen | It Department | 2
|  |  | 0.043113 | program a button to lead you to chatbot chat | It Department | 2 | a button at the top and end of the website that lead the customers into the chatbot
Analysis 2 | Chatbot Design 2.1 | 26 days
|  |  | 0.084039 | Identify platform | It Department | 3 | Private interface or hosted (Facebook Messenger, Telegram, Whatsapp)
|  |  | 0.084051 | Chatbot type | It Department | 4 | Menu/button-based, Linguistic Based (Rule-Based), Keyword recognition-based, Machine Learning, Hybrid model, Voice bots
|  |  | 0.084062 | Define the functionalities | It Department | 4 | Solve the problem if possible, otherwise offer an alternative. Email contact or redirection to phone operator
|  |  | 0.084074 | Entry source | It Department | 4 | Where customers come from and which are the most spoken languages
|  |  | 0.084086 | Recurring keywords | It Department | 3 | By interviewing the Customer Care on the most frequent Q&A, list down the moste frequent Keywords
|  |  | 0.084097 | Chatbot customization | It Department | 2 | Personality, Tov (Tone of voice)
|  |  | 0.084109 | Answers text | It Department | 2 | Dialogic, efficient, basic
|  |  | 0.08412 | Functional Analysis drawing | It Department | 5 | After having got all the business requirements, the BA draws the functional analysis to be used by the development teams
| Chatbot Back-end Developing 2.2 | 15 days
|  |  | 0.084734 | IT requirements | It Department | 5 | Given the IT platform, study the Functional Analysis in order to define the IT requirements and constraints
|  |  | 0.084745 | Coding | It Department | 5 | Process of writing down rules, iterations and exeptions using Programming code.
|  |  | 0.084757 | Quality Check | It Department | 5 | Being sure that the platform, code and data-flows work together without bugs
| Chatbot Front-end Developing 2.3 | 15 days
|  |  | 0.085428 | Create User Persona | Front-End Department | 8 | By studying Demographics, Psychology, Experience the F.E department creates the User persona
|  |  | 0.08544 | Create Bot Persona | Front-End Department | 7 | Given the User Persona, create the Bot Persona
0.085451
Test Release 3 | IT - Tests 3.1 | 20 days
|  |  | 0.12571 | check final development of chatbot | IT team | 5 | making sure everthing runs
|  |  | 0.12572 | ensure that both parties have excess to the chatbot | IT team | 4 | the IT team needs to have excess to the chatbot in order for updates to happen and for improvements, the customers need to be able to see the chatbot on the website
|  |  | 0.12573 | Set common questions that cutomer might ask | IT team | 4 | common qusetions that would be usually asked
|  |  | 0.12574 | ensure that the chatbot can understand variations of set questions | IT team | 4 | customers can ask the same question in various ways
|  |  | 0.12574 | redirect the customer to customer services or customer care if the chatbot is unable to assist or help with the customers quarries. | IT team | 3 | ensure that the customer comes first and is help no matter the question
| UAT -Test 3.2 | 24 days
|  |  | 0.1264 | create qusetions that volunteers need to ask the chatbot | IT team Customer care Customer services | 4 | variations of set question to ask chatbot, each volunnteer should ask 3 questions and recive 3 answers
|  |  | 0.12641 | find volunteers | IT team Customer care Customer services | 5 | volunteers need to complete at least 3 questions
|  |  | 0.12642 | give volunteers the answers to set questions | IT team Customer care Customer services | 3
|  |  | 0.12644 | get volunteers to run test | IT team Customer care Customer services | 3 | test should not take longer then 10-15 minutes
|  |  | 0.12645 | receive answers from vulunteers and analyze results | IT team Customer care Customer services | 3 | chatbot should be able answer or redirect and if not changes must be made
|  |  | 0.12646 | get volunteers to take a quesstionnaire for quality purpses | IT team Customer care Customer services | 3 | this questionnaire is only to check if the chatbot is effective
|  |  | 0.12647 | run test untill majority of vulunteers at satisfied | IT team Customer care Customer services | 3 | taboola strives for excellence
| C.Care Users Training 3.3 | 14 days
|  |  | 0.12709 | introduction to the new form of communication | IT team Customer care Customer services | 4 | thsi is the main and easy way for customer to communication with Taboola
|  |  | 0.1278 | how to access the new form of communication | IT team Customer care Customer services | 4 | basic understanding of the new website communcation
|  |  | 0.12851 | how to use the new form of communtication | IT team Customer care Customer services | 4 | how CC can help the customers
|  |  | 0.12921 | how to get assistance if need by IT team | IT team Customer care Customer services | 4
Pre - GO LIVE! 4 | Beta - Testing 4.1 | 14 days
|  |  | 0.16737 | Beta Testing | IT Depatment Business Analyst Team Development Team Customer Quality Manager |  | Get volunteering Customer to run Beta tests before the GO LIVE!
|  |  | 0.16738 | System requirrements review | IT Depatment Business Analyst Team Development Team Customer Quality Manager | 1 | starting with the system, making sure it has no errors in the website.
|  |  | 0.1674 | Design review | IT Depatment Business Analyst Team Development Team Customer Quality Manager | 1 | Making sure that the desing is user-friendly log in page and has all required elements to start.
|  |  | 0.16741 | Log in screen review | IT Depatment Business Analyst Team Development Team Customer Quality Manager | 1 | Making sure the log in proocess is done smoothly without any errors.
|  |  | 0.16742 | chatbot pop up access review | IT Depatment Business Analyst Team Development Team Customer Quality Manager | 1 | Make sure that the icon of the chatbot is moving while browsing the website, that the massage "how can i help you" pop out for the website visitor, and the button that leads to it is showing at the top and the end of website.
GO LIVE! 5 | Cheers ! | 2 days
|  |  | 0.20904 | Publishing the website | IT Depatment | 1 | Publishing the website
|  |  | 0.20905 | Final review | Quality Manager | 1 | Last review of the final project to make sure it is what we aim for the website visitor.
High | High risk in time estimation
Medium | Medium risk in time estimation
Low | Low risk in time wstimation